## Sheet1
|  |  | (January) |  | (Feburary) |  |  |  | (March)
|  |  | 19th-25th | 26th - 31st | 1st -8th | 9th - 15th | 16th - 22nd | 23rd - 28TH | 1st - 8th | 9th - 15th | 16th - 22nd | 23rd - 26th
Task | Start | End | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10
Dicuss project objective
Determine Programming Language
Define Work Development Cycle | D3 | D3
Anaylse existing systems | D2 | D4
Intermidate Report | D2 | D4
Create Initial GUI Design
Create Roundabout Prototype | D2 | D5
Test Rroundabout Prototype
Create T Junction Prototype
Test T Junction Protoype
Create Traffic Light Protoype | D4 | D5
Dicuss and Adjust GUI Design | D5 | D6
Development Of User Controls | D7 | D9
Final Report | D10 | D10
Presentation Pratice | D10 | D10